## Sheet1
Sr. No | Action Item | Action Owner | Start Date | Planned Completion date | Final Status | Comments
1 | Enter efforts into Service Now or if no access given then in the excel sheets. Leads appointed to collect and monitor the data to take inputs from their team members | All Test Team | 2015-03-25 | 2015-03-30 | Not Completed | In Progress by many, some have completed
2 | Extract test cases from regression pack as per the Release go live plan(shared before) | Akshay Kanadia Rehman Khan Abhinav Kashyap Shraddha Padelkar Ashish Sisodiya Rohit Pal Ravindra Gundale Sajesh Advilkar(Tariff) | 2015-03-26 | 2015-04-01 | Not Completed | In Progress by many, some have completed
3 | Add the below scenarios to Regression / Go live Plan 1. OBA registration with non logged in user 2. OBA registration with logged in user 3. OBA register with authentication token(ask Dhaval Panara) 4. OBA register with SOAPUI as mentioned below by Charlie(Speak to Abhijeet/ Shagun) to find out | Shraddha Padelkar | 2015-03-27 | 2015-03-27 | Not Completed | Last two scenarios are remaining. Conversation with Dhaval
4 | Learn to create stubs for Track and Trace and other apps. If not possible, make a summary of the issues, to be sent to Charlie | Abhinav Kashyap | 2015-03-27 | 2015-03-27 | Not Completed | talks with Abhijeet initiated some blockers observed
5 | Complete Automation of TRE journey as per Sachin provided traceability end to end test cases | Nirbhay Patil | 2015-04-10 | 2015-03-31 | Not Completed | In progress
6 | Complete automation of EIB production scenarios | Nirbhay Patil | 2015-04-01 | 2015-04-10 | Not Completed
7 | Add a column 'Actions Taken' in the summary of mail sent out daily on the behat test failures | Kiruba | 2015-03-25 | 2015-03-26 | Completed
8 | Add more scenarios into the production pack 1. From the exisiting list of scnenarios in jenkins 2. Whatever, the manual testers provide inputs | Kiruba | 2015-03-23 | 2015-04-10 | Completed | Some scenarois have been moved into the pack already
9 | Give Kiruba 3 scenarios per day to automate from the regression pack | Akshay Kanadia Rehman Khan Abhinav Kashyap Shraddha Padelkar Ashish Sisodiya Rohit Pal Ravindra Gundale Rakesh Khochare | 2015-03-23 | 2015-04-10 | Not Completed | Some testers have initiated the work with Kiruba- inprogress
10 | Give a knowledge transfer to test team and Environment team on how to run the various packs from Ashwini's machine | Kiruba / Nirbhay | 2015-03-23 | 2015-03-26 | Completed
11 | Create a good email reporting of Pass/ Fail status like the ECMT tool report sent out by Shagun | Nirbhay Patil | 2015-03-26 | 2015-04-05 | Not Completed
12 | All the tickets raised in RBCF, RMGI, RSR should be mapped to test case, if any, if not we need to mention and someone from that module will create it. | Pradnya / Akshay | 2015-03-26 | 2015-04-01 | Not Completed | Work started
13 | Add the Tariff scenarios into the below packs 1]Update Master Sheet https://coconet.capgemini.com/sf/go/doc6914865 All Master Sheet - (RMG_Testing_Traceability-Scenarios-Dashboards_Masterlist) 2] Update Smoke Test sheet https://coconet.capgemini.com/sf/go/doc6710854?nav=1 Smoke test Sheet - (RMG Combined Master Traceability Matrix) 3] Add your test cases to the below location: https://coconet.capgemini.com/sf/docman/do/listDocuments/projects.uk_ts_rmg_ebusiness/docman.root.work_area.testing_team.07_test_execution.regression.1_rml_scripts | Rakesh / Sajesh | 2015-04-01 | 2015-04-02 | Not Completed
14 | Update TRE scenarios to be tested in Go Live to Abhinav / Shraddha into the Go Live test plan, shared by me on email | Sachin Shah | 2015-03-26 | 2015-03-30 | Not Completed
15 | Add scenarios in our regression packs as per 'TRE lessons learnt and delivery assessment' | Sachin Shah | 2015-03-27 | 2015-03-31 | Not Completed
16 | To Organise Training sessions | Ravindra Gundale | 2015-03-20 | 2015-04-25 | Not Completed | In progress, some completed
17 | Download Xenu and install on your system | Akshay Kanadia Rehman Khan Abhinav Kashyap Shraddha Padelkar Ashish Sisodiya Rohit Pal Ravindra Gundale Sajesh Advilkar(Tariff) Sanith Shetty Hari Shaw | 2015-03-27 | 2015-03-31 | Not Completed
18 | Start regression scenairos pack Start assibility testing and Xenu for POLS | Sanith Shetty Hari Shaw | 2015-03-27 | 2015-04-05 | Not Completed